## Sheet1
Languages
Week 1 (18.05.2020-25.05.2020) | Planning | 3 days | Website Infrastructure Set-Up | Website Infrastructure Set-Up | Arnav | Python, JS, WEB
Week 2 (25.05.2020 - 1.06.2020) | Website Infrastructure Set-Up + Learning | 5 days | Calendar | Leave System | Lohit | Python, SQL, JS,WEB
Week 3 (1.06.2020 - 7.06.2020) | Calendar + Database | 3 days | Database Management | Calendar | Siddhant | Python,JS,WEB
Week 4 (8.06.2020 - 14.06.2020) | Time Tracker + Time Sheet Viewer | 5 days | Time Tracker | Client Customization | Shivam | Python, SQL, WEB
Week 5 (15.06.2020 - 21.06.2020) | TS Viewer + Leave System | 7 days | Time Sheet Viewer | Database Management
Week 6 (22.06.2020 - 28.06.2020) | Leave System + Notice Board | 7 days | Leave System | Data Analysis
Week 7 (29.06.2020 - 5.07.2020) | Hierarchy | 3 days | Notice Board | Hierarchy
Week 8 (5.07.2020 - 11.07.2020) | Client Customization + Data Analysis | 7 days | Hierarchy | Time Tracker
Week 9 (11.07.2020 - 18.07.2020) | Website Integration + Testing | 5 days | Client Customization | Time Sheet Viewer
|  | 3 days | Data Analysis | Notice Board
|  | 3 days | Website Integration | Testing
|  | 7 days | Testing | Website Integration
Week 2
Tuesday | Learning + Basic Infrastructure Design
Wednesday | Infrastructure (Django Project Set-Up with REST)
Thursday | Infrastructure (Django Project Set-Up with React, Urls, Basic Views)
Friday | Infrastructure (Django - Models, Complex Views)
Saturday | Review, Basic Testing
Sunday | Blank
Week 3
Monday | React learning + Basic DB Setup
Tuesday | Calendar Development + AWS Setup
Wednesday | Calendar Frontend + AWS
Thursday | Calendar Integration with Django + DB Design
Friday | Total Integration
Saturday | Review + Showing Sir
Sunday | Planning