## Sheet1
Languages
Week 1 (18.05.2020-25.05.2020) | Planning | 3 days | Website Infrastructure Set-Up | Website Infrastructure Set-Up | Arnav | Python, JS, WEB
Week 2 (25.05.2020 - 1.06.2020) | Website Infrastructure Set-Up + Learning | 5 days | Calendar | Leave System | Lohit | Python, SQL, JS,WEB
Week 3 (1.06.2020 - 7.06.2020) | Calendar + Database | 3 days | Database Management | Calendar | Siddhant | Python,JS,WEB
Week 4 (8.06.2020 - 14.06.2020) | Time Tracker + Time Sheet Viewer | 5 days | Time Tracker | Client Customization | Shivam | Python, SQL, WEB
Week 5 (15.06.2020 - 21.06.2020) | Time Sheet Viewer | 7 days | Time Sheet Viewer | Database Management
Week 6 (22.06.2020 - 28.06.2020) | User Model | 7 days | Leave System | Data Analysis
Week 7 (29.06.2020 - 5.07.2020) | Permissions | 3 days | Notice Board | Hierarchy
Week 8 (5.07.2020 - 11.07.2020) | Notice Board | 7 days | Hierarchy | Time Tracker
Week 9 (11.07.2020 - 17.07.2020) | Leave System | 5 days | Client Customization | Time Sheet Viewer
Week 10 (18.07.2020-24.07.2020) | Client Customization | 3 days | Data Analysis | Notice Board
Week 11 (25.07.2020 - 31.07.2020) | Data Analysis | 3 days | Website Integration | Testing
Week 12 (01.08.2020 - 07.08.20) | Website Integration | 7 days | Testing | Website Integration
Week 13 (08.08.2020 - 18.08.2020) | Testing
Week 2
Tuesday | Learning + Basic Infrastructure Design |  | SQL
Wednesday | Infrastructure (Django Project Set-Up with REST) |  | Daily Activity - Per User
Thursday | Infrastructure (Django Project Set-Up with React, Urls, Basic Views) |  | All User Data - Secure
Friday | Infrastructure (Django - Models, Complex Views) |  | Leave Data - Per User
Saturday | Review, Basic Testing
Sunday | Blank
Week 3
Monday | React learning + Basic DB Setup
Tuesday | Calendar Development + AWS Setup
Wednesday | Calendar Frontend + AWS
Thursday | Calendar Integration with Django + DB Design
Friday | Total Integration
Saturday | Review + Showing Sir
Sunday | Planning
Week 4
Monday | Setup + Sid needs to learn Redux | 2 days | Subroutine-3
Tuesday | S3 + S5/S6 | 3 days | S5 & S6
Wednesday | S3 + S5/S6 | 1 day | S7
Thursday | S3 + S5/S6 | 2 days | S8
Friday | Middleware
Saturday | S8 + S7
Sunday | S8 + S7 + Review + Planning
Week 5
User Creation and Administration | LLU
HLU
View TimeSheet | 1. SEARCH BAR
Choices Model Modification | > Reflection in GUI
Week 6
Integrate User Model with Existing Apps | TimeTracker | Arnav, Lohit
| Calendar | Shivam and Sid
HomeScreen | The options
Arnav and Shivam | User info
Notice Board
Week 7
Manage permissions within the current user model |  | Lohit & Sid
Integrate User Model with Existing Apps | TimeTracker | Arny + Shivam
Calendar
Settings Panel |  | Sid + Shivam
Hierarchy With Existing User Levels |  | Lohit + Arnav
Week 8
Research and Implementation | Inter-UserType
Intra-UserType
Inter-user relationship
Notice Board | Fetch Choices API
Leave System Card
Integration with User
Create Assignments